## 1. Specification CL
Specification checklist (Phase 1)
Product_Name |  | Rev 1.0
Document | Responsible | Filename | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
Design requirement specification |  | CCxx10_Demonstration_Kit_Specification_1_0.doc | x
Test specification |  | CCxx10_Demonstration_Kit_Specification_1_0.doc | x | Can be written before Phase 4
Production test specification |  | CCxx10_Demonstration_Kit_Specification_1_0.doc | x | Can be written before or during Phase 4
x
Review date
Tasks after review OK |  |  | OK (='x') | Comments | Date
Schematic design can start |  |  | x
Send list of components with long lead time to Operations |  |  | x
Update design specification if needed
Desing ready for next phase |  |  | x

## 2. Schematic CL
Schematic checklist (Phase 2)
Product_Name | Rev x.y
Designer: XXX | A0190XXX
Tasks by designer before schematic design |  | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
Locate updated Library at C:\Cadstar\LIBRARY |  | x
Copy the project folder template from C:\Cadstar\TILPW\Templates\Project_Folder_Template to Product Name design folder |  | x | Doc and Cadstar folders. Templates for Design_Change_List.xls, Readme.txt and Partlist.xls
Check Design Change List for updates |  | x | Use Design_Change_List.xls template
Detailed review of all new components added to the CadStar library |  | x
Document | Filename | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
Circuit diagram | CC1110DEMO_SCHEMATIC_0_1.pdf | x
Partlist | Partlist.xls | x | Use Partlist.xls template
Document archive file (all files above) | Product_Name_REVIEW_1_0.zip
CadStar checklist
Schematic | CC1110DEMO_0_1.sch | x
ERC (Electrical Rules Check) | ERC.rep | x
Unused components report | Unused_components.rep | x
Review date
Tasks by designer after review OK |  | OK (='x') | Comments | Date
PCB design can start |  | x
Send partlist to Operations for component purchase
Update design specification if needed
Design ready for next phase |  | x

## 3. Layout CL
Layout checklist (Phase 3)
SmartRFCC2510 | Rev 1.1
Designer: PEH | A0132597
Tasks before layout design |  | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
In Readme.txt change - PCB name and revision - Date - PCB description - Board thickness |  | x | Use Readme.txt template
Locate Library to C:\Cadstar\LIBRARY |  | x | Use workspace file template
Reload components from library |  | x
Locate colour files to C:\Cadstar\TILPW\Colours |  | x | Use workspace file template
Locate Selection files to C:\Cadstar\TILPW\Selections |  | x | Use workspace file template
Check Design Change List for updates |  | x | Use Design_Change_List.xls template
All electronic Gerber files shall be 1:1 at offset (x,y) = (1000, 1000) mils |  | x
CadStar checklist
DRC (Design Rules Check) | DRC.rep | x
Board status | Board_status.rep
Routing completion | Routing_completion.rep | x
Gerber Batch prosess | Gerber.rep | x | Drill and NC Drill info in batch report file
Unused components report | Unused_components.rep
Design Change List | Productname_Design_Change_List_X_X |  | Use Design_Change_List.xls template
Review date
Reference design documentation checklist
Document | Filename | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
Document overview | Readme.txt | x
Layer 1 | L1.SPL | x
Layer 2 | L2.SPL | x
Layer 3 | L3.SPL
Layer 4 | L4.SPL
Solder stop component side | STOPCOMP.SPL | x
Solder stop solder side | STOPSOLD.SPL | x
Silkscreen component side | SILKCOMP.SPL | x
Silkscreen solder side | SILKSOLD.SPL | x
Solder paste component side | PASTCOMP.SPL | x
Solder paste solder side | PASTSOLD.SPL | x
Assembly component side | ASSYCOMP.SPL | x
Assembly solder side | x | x | Gerber file shall be transparent PDF file shall be mirrored
Drill/mechanical drawing | DRILL.SPL | x
NC drill through-hole | NCDRILL.SPL | x
Gerber batch process | GERBER.REP | x
Part List | Product_Name_PARTLIST.XLS | x | Use Partlist.xls template
Aperture table | Ext_Gerber.USR | x
NC drill device file | CNC.USR | x
Pick and place component side | P&PCOMP.REP | x
Pick and place solder side | P&PSOLD.REP | x
Circuit diagram | CC2510DEMO_SCHEMATIC_1_1.pdf | x
Layout diagram | CC2510DEMO_LAYOUT_1_1.PDF | x | Generated by Viewmate (one file for all layers)
Cadstar schematic file | CC2510DEMO_1_1.scm | x
Cadstar schematic archive | CC2510DEMO_1_1.csa | x
Cadstar layout file | CC2510DEMO_1_1.pcb | x
Cadstar PCB archive | CC2510DEMO_1_1.cpa | x
Optional Document | File name
Panel description | Product_Name_Panel.pdf |  | Default NA
Assembly note | Product_Name_Assembly_Note_1_0.pdf |  | Default NA
Document archive file (all files above) | SmartRFCC25100rev1_1.zip
Task by designer after review OK |  | OK (='x') | Comments | Date
inform Operation that PCB prototype serie can start
Inform responible for test that design is completed
Open gerber files in gerber viewer and verify design
Design ready for next phase

## 4. TEST
Test checklist (Phase 4)
Product_Name | Rev 1.0
Test Engineers: XXX | a0190XXX
Task byTest Engineer before review |  |  | OK (='x') | Comments | Date
Test according to test specification
Verify production test specification
Desing ready for production
Document | Author | Filename | OK (='x') | Comments | Review OK (='x') | Reviewer's initials
Test report | Test Engineer | Product_name.pdf
Review date
Task byTest Engineer after review OK |  |  | OK (='x') | Comments | Date
Update design specification if needed
Update design change list if needed
Update production test specification if needed
Desing ready for production